## Instructions
Instructions for Tax Credit Assistance Program (TCAP) and Tax Credit Exchange (Monetization) Program Underwriting / Closing Schedule
Applications for Tax Credit Assistance Program (TCAP) funds and Tax Credit Exchange (Monetization) Program funds must include an Underwriting / Closing Schedule substantially similiar to the following. Applicants may add activities and adjust time, but you must show how they can be ready to close within 60 days of the submission date (May 1, 2009 in the case of Round 1 Applications). Applicants may use MS Project or any other project scheduling software they may have or they may use Excel. The intent of the schedule is to demonstrate to DCA how you will get from Application date to closing (60 days). For example, those Applicants turning in Applications May 1, 2009 will be required to provide a schedule showing how they will be ready to start July 1, 2009. Applicants will be held accountable for substantially complying with their schedule and any material adverse deviation from the schedule in the sole judgement of DCA may result in the Application being deferred from processing in favor of other Applications that have demonstrated the ability to comply with their schedule.

## Schedule
Tax Credit Assistance Program/Tax Credit Exchange Program - Application Underwriting/Closing Schedule | [36 empty] | Tax Credit Assistance Program/Tax Credit Exchange Program - Application Underwriting/Closing Schedule
|  |  | TCAP Round: | [36 empty] | TCAP Round: |  |  | 0
|  |  | Applicant: | [36 empty] | Applicant: |  |  | 0
|  |  | Project: | [36 empty] | Project: |  |  | 0
|  | Duration | Start | End |  | May | [32 empty] | Duration | Start | End |  | June
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Submit Phase I Documentation |  | 0 | 2009-05-01 | 2009-05-01 | [32 empty] | Submit Phase I Documentation |  | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
Submit Phase II Documentation |  | 14 | 2009-05-01 | 2009-05-15 | [32 empty] | Submit Phase II Documentation |  | 14 | 2009-05-01 | 2009-05-15 | bar: May 2 to May 15
Submit Phase III Documentation |  | 31 | 2009-05-01 | 2009-06-01 | [32 empty] | Submit Phase III Documentation |  | 31 | 2009-05-01 | 2009-06-01 |  | III
Financial/Market Activities/Goals | [36 empty] | Financial/Market Activities/Goals
| Revised Core Application | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Revised Core Application | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Preliminary TCAP Commitment | 9 | 2009-05-01 | 2009-05-10 | [33 empty] | Preliminary TCAP Commitment | 9 | 2009-05-01 | 2009-05-10 | bar: May 2 to May 10
| Resolution of all DCA Underwriting Issues | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Resolution of all DCA Underwriting Issues | 31 | 2009-05-01 | 2009-06-01 | bar: May 2 to May 31
| Firm TCAP commitment | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Firm TCAP commitment | 31 | 2009-05-01 | 2009-06-01
| Close & Commence Construction | 61 | 2009-05-01 | 2009-07-01 | [33 empty] | Close & Commence Construction | 61 | 2009-05-01 | 2009-07-01
| Preliminary Equity Commitment | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Preliminary Equity Commitment | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Procure Firm Equity Commitment | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Procure Firm Equity Commitment | 0 | 2009-05-01 | 2009-05-01 | bar: May 2 to May 15
| Negotiation of Preliminary LPA | 14 | 2009-05-01 | 2009-05-15 | [33 empty] | Negotiation of Preliminary LPA | 14 | 2009-05-01 | 2009-05-15 | bar: May 2 to May 15
| Negotiation of Final LPA | 14 | 2009-05-01 | 2009-05-15 | [33 empty] | Negotiation of Final LPA | 14 | 2009-05-01 | 2009-05-15 |  | III | bar: May 16 to May 31
| Close & Commence Construction | 61 | 2009-05-01 | 2009-07-01 | [33 empty] | Close & Commence Construction | 30 | 2009-06-01 | 2009-07-01
| Preliminary Debt Commitment(s) | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Preliminary Debt Commitment(s) | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Procure Firm Debt Commitment | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Procure Firm Debt Commitment | 31 | 2009-05-01 | 2009-06-01 |  | III
| Negotiate Loan Documents | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Negotiate Loan Documents | 31 | 2009-05-01 | 2009-06-01 |  | III
| Close & Commence Construction | 61 | 2009-05-01 | 2009-07-01 | [33 empty] | Close & Commence Construction | 61 | 2009-05-01 | 2009-07-01
| Appraisal Shared between Lenders | 30 | 2009-05-01 | 2009-05-31 | [33 empty] | Appraisal Shared between Lenders | 30 | 2009-05-01 | 2009-05-31
| Market Study Up-date | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Market Study Up-date | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Resolution of any market related Issues | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Resolution of any market related Issues | 31 | 2009-05-01 | 2009-06-01 | bar: May 2 to May 15
Development/Construction Activities/Goals | [36 empty] | Development/Construction Activities/Goals
| Design/Development Plans | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Design/Development Plans | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Complete Final Construction Ready Plans | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Complete Final Construction Ready Plans | 31 | 2009-05-01 | 2009-06-01 |  | III
| Energy Efficiency Plan/Proposal | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Energy Efficiency Plan/Proposal | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Incorporation of Energy Efficiency Plan | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Incorporation of Energy Efficiency Plan | 31 | 2009-05-01 | 2009-06-01
| DCA/Lender Front-End Review | 40 | 2009-05-01 | 2009-06-10 | [33 empty] | DCA/Lender Front-End Review | 40 | 2009-05-01 | 2009-06-10
| Resolution of Design/Construction Issues | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Resolution of Design/Construction Issues | 31 | 2009-05-01 | 2009-06-01
| If Rehab, Physical Needs Assessment | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | If Rehab, Physical Needs Assessment | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Selection of General Contractor | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Selection of General Contractor | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Obtain Approval of Contractor | 14 | 2009-05-01 | 2009-05-15 | 2009-05-16 | [32 empty] | Obtain Approval of Contractor | 14 | 2009-05-01 | 2009-05-15 | 2009-05-16 | bar: May 2 to May 15
| Draft of Construction Contract | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Draft of Construction Contract | 31 | 2009-05-01 | 2009-06-01 | bar: May 2 to May 15
| Final Executed/Approved Contract | 45 | 2009-05-01 | 2009-06-15 | [33 empty] | Final Executed/Approved Contract | 45 | 2009-05-01 | 2009-06-15 |  | III
| Preliminary Schedule of Values | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Preliminary Schedule of Values | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Final Schedule of Values | 14 | 2009-05-01 | 2009-05-15 | [33 empty] | Final Schedule of Values | 14 | 2009-05-01 | 2009-05-15 | bar: May 2 to May 15
| Preliminary Construction Schedule | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Preliminary Construction Schedule | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Final Construction Schedule | 14 | 2009-05-01 | 2009-05-15 | [33 empty] | Final Construction Schedule | 14 | 2009-05-01 | 2009-05-15 | bar: May 2 to May 15
| Environmental Up-Date | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Environmental Up-Date | 0 | 2009-05-01 | 2009-05-01 | bar: May 1
| Resolution of any Environmental issues | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Resolution of any Environmental issues | 31 | 2009-05-01 | 2009-06-01
| Current Boundary Survey | 0 | 2009-05-01 | 2009-05-01 | [33 empty] | Current Boundary Survey | 0 | 2009-05-01 | 2009-05-01 | bar: May 2 to May 15
| Resolution of any Survey issues | 31 | 2009-05-01 | 2009-06-01 | [33 empty] | Resolution of any Survey issues | 31 | 2009-05-01 | 2009-06-01
| DCA Pre-Construction Conference | 45 | 2009-05-01 | 2009-06-15 | [33 empty] | DCA Pre-Construction Conference | 45 | 2009-05-01 | 2009-06-15
| DCA Davis Bacon Conference | 45 | 2009-05-01 | 2009-06-15 | [33 empty] | DCA Davis Bacon Conference | 45 | 2009-05-01 | 2009-06-15
Legal/Compliance Activities/Goals | [36 empty] | Legal/Compliance Activities/Goals
| Preparation/Negotiation of Loan Documents | 55 | 2009-05-01 | 2009-06-25 | [33 empty] | Preparation/Negotiation of loan Documents | 55 | 2009-05-01 | 2009-06-25
| Review of Title/Resolution of Issues | 55 | 2009-05-01 | 2009-06-25 | [33 empty] | Review of Title/Resolution of Issues | 55 | 2009-05-01 | 2009-06-25
| Review of Insurance/Resolution of Issues | 55 | 2009-05-01 | 2009-06-25 | [33 empty] | Review of Insurance/Resolution of Issues | 55 | 2009-05-01 | 2009-06-25
| Closing | 61 | 2009-05-01 | 2009-07-01 | [33 empty] | Closing | 61 | 2009-05-01 | 2009-07-01
Closing Date Set
Weekly Closing Conference Calls
Formulas:
Start = [Start]
End = [End]